## Sheet1
Build and Test Plan | Testers: Joshua Mularczyk and Christian Williams
Steps: | Description: | Column3 | Column4 | Column5 | Column6 | Column7 | Column8 | Column9 | Column10 | Column11 | Column12
1 | Unbox and Take Inventory of Parts from Digikey and Amazon
2 | Designate Storage area (Analog Lab)
3 | Take Solar Panel outside and test: Output Voltage(open Circuit), Output Current(short circuit), maximum power point (using a resistor(Voc/Isc) to best represent our load, and Calculate Output Power | Column3: Expected Voltage: 9V; Column4: Expected Current: 1.1 Amps; Column5: Expected Power: 10W
4 | Construct the Circuit by soldering onto PCB
5 | Inspect all solder connection under the Microscope to check for errors
6 | Check any parts with ohm meter
7 | Plug in power souce and watch current (if it peggs out then immediately shut it off
8 | Turn on the power source again and check output voltage by using the through hole connections before soldering on the USB connector and a load resistor.
9 | If output voltage is at or near 5V then go though and check any other values.
10 | Solder on solar panel